## Sheet1
SmartMauzo Review
No | Module | Problem | Fix Status | Comment | Responsible Person to fix | End Date
| Register | 1.View(subscripty_type) | Problem was fixed
|  | 2.in case user do mistake in filling form system not redirect user to the field | Not fixed | Problem must be fixed
| Settings | Null |  | Good
| Products | 1.Add basic units eg basic unit for eggs(Allow user to add his own unit) | Not fixed | Problem must be fixed
|  | 2.Add new product in Purchase an order does not work | Not fixed | We have to fix it | Elifuraha | 2023-04-11
|  | 3. Product not added successful without image | Problem was fixed
|  | 4. View of the page Purchase orders is not good | Not fixed | We have to fix it
|  | 5. Add purchase item does not work | Not fixed | We have to fix it
| Add User | 1.Poor User interface | Not fixed | Create a good view
|  | 2.Unessessary User Roles | Not fixed | Delete uder role which is not used
| POS | 1.Discount does not applied | Not fixed | We have to fix it
| On sales return | it allows user to enter a negative value on amount return
| VFD | Not working | Not fixed | Remove if not in use
| Price List | 1.Use a good icon | Not fixed | Select a good icon
| Inventory Report | 1.Select product not working | Not fixed | Fix it
| Supplier Account | 1.Actions(Delete and Edit) does not work | Not fixed | Fix it
| Expenses | 1.Delete multiple expenses does not work | Not fixed | We have to fix it | Isaya | 2023-04-11
|  | 2.Cancel button does not work in edit expense categories | Not fixed | We have to fix it
| Cash Inflow | 1.Amount in new cash in can not exeed 999,999.99 | Not fixed | We have to fix it
| Payment | 1.Does not work | Not fixed | We have to fix it
| General | 1. Display selected date | Not fixed | Fix it
|  | 2.Pop up massage should appear clear | Not fixed
|  | 3.Search (Type Ahead) | Not fixed
|  | 4.Download exel sample | Not fixed
| Dashboard ( Business type change) | show input strings
Select stores input should be same size
| Total sales, collections and debts cards | should be of bigger size to fit the amount numbers
| User guide | 1.Does not work | Not fixed | We have to fix it
| Support | 1.Does not work | Not fixed | We have to fix it